## Some Hints and Explanations
some hints and explanations concerning this template
About this template:
This template is supposed to help you developing your project schedule.
On the "Milestones + Packages" Sheet you may input your milestones and subtasks with all necessary information (although you may add some columns, of course).
The very first column defines the type of this row: (M) defines Milestone, (S),(S1),(S2),(S3) subtasks (the number currently only defines its color in the gantt chart. A milestone should be of duration "1" (meaning it's a single date).
Also, you may enter the team members' names in Cells H2:L2, which should suffice in order to update the remaining sheets.
The "Time Sheets TM1" - "Time Sheet TM5" may be used to keep track of your workload. For each team member, mark the assigned tasks on the "Milestones + Packages" Sheet in columns H to L by inserting an "x". You can then choose those tasks in the first column "Task" in the respective table on the time sheet via a drop down menu. Be careful to find a way of updating your individual work loads that avoids file version conflicts of your .xlsx File.
You may use the "Gantt Chart" sheet for printing your schedule.
There is one unpleasant issue: Moving rows may cause Excel to adapt referenced formulas in the gantt chart. You may therefore prepare (and order) the schedule on a temporary sheet and then copy it into the main sheet. Also, you must take care to only copy values (no formattting) when doing so.
First steps:
We suggest the following steps:
1) Enter your team members names in the cells H2:L2 on "Milestones + Packages", you may delete the 5th one if not needed.
2) Switch to the "temporary" sheet to develope your schedule. Reason: You can change any row contents in "Milestones + Packages", but you will not be able to permute rows nor to insert new ones. Define your milestones and subtasks, arrange them in a reasonable order.
3) Copy the "temporary" cells to the "Milestons + Packages" sheet, but only by value (such that no format rules are overwritten). In order to do so, mark the respective cells, copy them, mark the first cell on the "Milestones + Packages" sheet, and select "Value (V)" in the context menu (or press "V").
4) You may adapt colors in the gantt chart by changing the A-column entry.
5) Print your gantt chart.
Of course, feel free to adapt and improve and correct this template. If you can come up with something particularly useful, it would be nice to let us know so that future case studies may benefit as well!

## Milestones + Packages
Milestones & Workpackages
Typ | Name | Description | Result | Start | Duration (days) | Responsible | Fin | Stan | Roland | Stefan | Jakob
(M) | Brainstorming phase |  | First Idea, of what we want to do | 2015-04-20 | 1 |  | x | x | x | x | x
(S) | Choose ML Application |  | Application | 2015-04-13 | 7 | all | x | x | x | x | x
(S2) | Set up Project Mgmt Tools | Research and set up Communication, Development und Versioning tools | Working Environment | 2015-04-13 | 7 | Stefan |  |  |  | x
(M) | Project Schedule | Develop a project schedule for the whole project. This contains all milestones and the corresponding subtasks in a SMART way. |  | 2015-04-22 | 1 |  | x | x | x | x | x
(S) | Define Milestones & Packages | Define the project's big milestones and put them into this plan. Define the corresponding tasks in a SMART way (this includes time issues, responsibilities, exact task descriptions, description of their result). Discuss whether you need to adapt this template for your individual needs (maybe more columns to describe a task?) | Milestones and Taks are put into your this schedule. | 2015-04-20 | 1 | Stefan | x | x | x | x | x
(S2) | Revise and Finalize Project Plan | Revise your project plan, and send final Version to Andre. | Result --> Andre | 2015-04-21 | 2 | Stefan | x | x | x | x | x
(M) | Poster |  | Poster sent to advisors for printing. Concept and material for booth ready. | 2015-05-10 | 1 | Fin, Jakob
(S1) | Poster Macrodesign |  | Idea of what the poster should look like | 2015-04-22 | 1 | All | x | x | x | x | x
(S2) | Work on Poster Concept |  |  | 2015-04-22 | 5 | Fin, Jakob | x |  |  |  | x
(S1) | Discuss and Finalize Poster Concept |  |  | 2015-04-27 | 1 | Fin, Jakob | x | x | x | x | x
(S2) | Implementation |  | Finalized Poster v1 | 2015-04-27 | 2 | Fin, Jakob | x | x | x | x | x
(S) | Internal Poster Presentation |  | Presentation to Advisor and other Groups | 2015-05-04 | 1 | Fin, Jakob | x | x | x | x | x
(S1) | Revise and Finalize Poster |  | Final Poster | 2015-05-04 | 6 | Fin, Jakob | x | x | x | x | x
(M) | Booth | Develop the booth for the presentation | Booth | 2015-05-11 | 1 | Fin, Jakob
(S) | Define and Collect Necessary Materials |  | All materials ready | 2015-04-20 | 19 | Fin, Jakob | x |  |  |  | x
(S1) | Design UX | Design user experience, think through the workflow | Final Concept | 2015-05-01 | 10 | Fin, Jakob | x | x | x | x | x
(S2) | Finalize Booth |  | Booth | 2015-05-10 | 2 | Fin, Jakob | x | x | x | x | x
(M) | Prototype "App" | Implementation of Eigenface software using existing packages | Working prototype to show at exhibition booth | 2015-05-29 | 1 | Roland, Stan | x | x | x | x | x
(S) | Proof of Concept | Design and implement first version | First Working Program | 2015-04-20 | 7 | Roland, Stan |  | x | x
(S1) | Dataset | Research, Acquire and Clean a dataset for our use | Dataset | 2015-04-20 | 7 | Stefan |  |  |  |  | x
(S2) | Further development | Iterate on the first version | Working program to show at boot | 2015-04-27 | 30 | ? | x | x | x | x | x
(M) | Algorithms | Implement algorithms from Literature, test, tweak, benchmark | Working Implementations of algorithms, benchmarking against other methods | 2015-06-25 | 1 | ? | x | x | x | x | x
(S) | Introduction Tutorials | Prepare a short tutorial on Eigenfaces/Dictionary Learning and present to the group | Short presentations | 2015-04-20 | 3 | Roland, Stan | x | x
(S3) | Literature Review | Read, understand and summarize relevant papers. | relevant knowledge for further project work | 2015-05-01 | 30 | all | x | x | x | x | x
(S) | Model Selection | Get informed about machine Learning, select a few applicable models for our application | know how, model selection | 2015-05-01 | 30 | ? | x | x | x | x | x
(S1) | General Implementation | Implement relevant stochastic algorithms from literature in general form | working general version | 2015-05-29 | 11 | ? | x | x | x | x | x
(S2) | Tweaking for application | Improve and adapt the algorithms for the chosen application, implement interfaces between app, algorithms and ML models | Final Algorithm Implementations | 2015-06-01 | 20 | ? | x | x | x | x | x
(S3) | Testing, Benchmarking | Tweaking models and algorithms, compare algorithms, analytical work | First Results | 2015-06-15 | 10 | all | x | x | x | x | x
(M) | Midterm Presenation |  | Presenting the status quo. | 2015-05-27 | 1 | all | x | x | x | x | x
(S) | Prepare Presentation | see title | Presentation | 2015-05-18 | 7 | all | x | x | x | x | x
(M) | Final Workshop |  | Presentation of your project's results. | 2015-07-11 | 1
(S) | Compile Results | Compile and visualize results of analysis | Results/Charts etc | 2015-06-20 | 8 | all | x | x | x | x | x
(S2) | Abstract |  | Hand in abstract by June 28th. | 2015-06-28 | 1 |  | x | x | x | x | x
(S3) | Prepare Presentation |  |  | 2015-06-28 | 13 |  | x | x | x | x | x

## Gantt Chart
Gantt Chart
[5 empty] | Hidden Milestone | KW 16 | [6 empty] | KW 17 | [6 empty] | KW 18 | [6 empty] | KW 19 | [6 empty] | KW 20 | [6 empty] | KW 21 | [6 empty] | KW 22 | [6 empty] | KW 23 | [6 empty] | KW 24 | [6 empty] | KW 25 | [6 empty] | KW 26 | [6 empty] | KW 27 | [6 empty] | KW 28 | [6 empty] | KW 29
[6 empty] | 2015-04-13 | [6 empty] | 2015-04-20 | [6 empty] | 2015-04-27 | [6 empty] | 2015-05-04 | [6 empty] | 2015-05-11 | [6 empty] | 2015-05-18 | [6 empty] | 2015-05-25 | [6 empty] | 2015-06-01 | [6 empty] | 2015-06-08 | [6 empty] | 2015-06-15 | [6 empty] | 2015-06-22 | [6 empty] | 2015-06-29 | [6 empty] | 2015-07-06 | [6 empty] | 2015-07-13
[6 empty] | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S | M | D | M | D | F | S | S
hidden date | time axis 2015-04-13 to 2015-07-19
Brainstorming phase | 2015-04-20 | 2015-04-20 |  | Fin Stan Roland Stefan Jakob | 2015-04-20
Choose ML Application | 2015-04-13 | 2015-04-19 | all | Fin Stan Roland Stefan Jakob
Set up Project Mgmt Tools | 2015-04-13 | 2015-04-19 | Stefan | Stefan
Project Schedule | 2015-04-22 | 2015-04-22 |  | Fin Stan Roland Stefan Jakob | 2015-04-22
Define Milestones & Packages | 2015-04-20 | 2015-04-20 | Stefan | Fin Stan Roland Stefan Jakob
Revise and Finalize Project Plan | 2015-04-21 | 2015-04-22 | Stefan | Fin Stan Roland Stefan Jakob
Poster | 2015-05-10 | 2015-05-10 | Fin, Jakob |  | 2015-05-10
Poster Macrodesign | 2015-04-22 | 2015-04-22 | All | Fin Stan Roland Stefan Jakob
Work on Poster Concept | 2015-04-22 | 2015-04-26 | Fin, Jakob | Fin Jakob
Discuss and Finalize Poster Concept | 2015-04-27 | 2015-04-27 | Fin, Jakob | Fin Stan Roland Stefan Jakob
Implementation | 2015-04-27 | 2015-04-28 | Fin, Jakob | Fin Stan Roland Stefan Jakob
Internal Poster Presentation | 2015-05-04 | 2015-05-04 | Fin, Jakob | Fin Stan Roland Stefan Jakob
Revise and Finalize Poster | 2015-05-04 | 2015-05-09 | Fin, Jakob | Fin Stan Roland Stefan Jakob | 2015-05-04
Booth | 2015-05-11 | 2015-05-11 | Fin, Jakob
Define and Collect Necessary Materials | 2015-04-20 | 2015-05-08 | Fin, Jakob | Fin Jakob
Design UX | 2015-05-01 | 2015-05-10 | Fin, Jakob | Fin Stan Roland Stefan Jakob
Finalize Booth | 2015-05-10 | 2015-05-11 | Fin, Jakob | Fin Stan Roland Stefan Jakob | 2015-05-10
Prototype "App" | 2015-05-29 | 2015-05-29 | Roland, Stan | Fin Stan Roland Stefan Jakob
Proof of Concept | 2015-04-20 | 2015-04-26 | Roland, Stan | Stan Roland
Dataset | 2015-04-20 | 2015-04-26 | Stefan | Jakob
Further development | 2015-04-27 | 2015-05-26 | ? | Fin Stan Roland Stefan Jakob | 2015-04-27
Algorithms | 2015-06-25 | 2015-06-25 | ? | Fin Stan Roland Stefan Jakob
Introduction Tutorials | 2015-04-20 | 2015-04-22 | Roland, Stan | Fin Stan
Literature Review | 2015-05-01 | 2015-05-30 | all | Fin Stan Roland Stefan Jakob
Model Selection | 2015-05-01 | 2015-05-30 | ? | Fin Stan Roland Stefan Jakob
General Implementation | 2015-05-29 | 2015-06-08 | ? | Fin Stan Roland Stefan Jakob
Tweaking for application | 2015-06-01 | 2015-06-20 | ? | Fin Stan Roland Stefan Jakob
Testing, Benchmarking | 2015-06-15 | 2015-06-24 | all | Fin Stan Roland Stefan Jakob | 2015-06-15
Midterm Presenation | 2015-05-27 | 2015-05-27 | all | Fin Stan Roland Stefan Jakob
Prepare Presentation | 2015-05-18 | 2015-05-24 | all | Fin Stan Roland Stefan Jakob | 2015-05-18
Final Workshop | 2015-07-11 | 2015-07-11
Compile Results | 2015-06-20 | 2015-06-27 | all | Fin Stan Roland Stefan Jakob
Abstract | 2015-06-28 | 2015-06-28 |  | Fin Stan Roland Stefan Jakob
Prepare Presentation | 2015-06-28 | 2015-07-10 |  | Fin Stan Roland Stefan Jakob

## task extraction (hidden)
Fin | Fin | Stan | Stan | Roland | Roland | Stefan | Stefan | Jakob | Jakob
other | other | other | other | other | other | other | other | other | other
Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase | Brainstorming phase
Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application | Choose ML Application
| Project Schedule |  | Project Schedule |  | Project Schedule | Set up Project Mgmt Tools | Set up Project Mgmt Tools |  | Project Schedule
Project Schedule | Define Milestones & Packages | Project Schedule | Define Milestones & Packages | Project Schedule | Define Milestones & Packages | Project Schedule | Project Schedule | Project Schedule | Define Milestones & Packages
Define Milestones & Packages | Revise and Finalize Project Plan | Define Milestones & Packages | Revise and Finalize Project Plan | Define Milestones & Packages | Revise and Finalize Project Plan | Define Milestones & Packages | Define Milestones & Packages | Define Milestones & Packages | Revise and Finalize Project Plan
Revise and Finalize Project Plan | Poster Macrodesign | Revise and Finalize Project Plan | Poster Macrodesign | Revise and Finalize Project Plan | Poster Macrodesign | Revise and Finalize Project Plan | Revise and Finalize Project Plan | Revise and Finalize Project Plan | Poster Macrodesign
| Work on Poster Concept |  | Discuss and Finalize Poster Concept |  | Discuss and Finalize Poster Concept |  | Poster Macrodesign |  | Work on Poster Concept
Poster Macrodesign | Discuss and Finalize Poster Concept | Poster Macrodesign | Implementation | Poster Macrodesign | Implementation | Poster Macrodesign | Discuss and Finalize Poster Concept | Poster Macrodesign | Discuss and Finalize Poster Concept
Work on Poster Concept | Implementation |  | Internal Poster Presentation |  | Internal Poster Presentation |  | Implementation | Work on Poster Concept | Implementation
Discuss and Finalize Poster Concept | Internal Poster Presentation | Discuss and Finalize Poster Concept | Revise and Finalize Poster | Discuss and Finalize Poster Concept | Revise and Finalize Poster | Discuss and Finalize Poster Concept | Internal Poster Presentation | Discuss and Finalize Poster Concept | Internal Poster Presentation
Implementation | Revise and Finalize Poster | Implementation | Design UX | Implementation | Design UX | Implementation | Revise and Finalize Poster | Implementation | Revise and Finalize Poster
Internal Poster Presentation | Define and Collect Necessary Materials | Internal Poster Presentation | Finalize Booth | Internal Poster Presentation | Finalize Booth | Internal Poster Presentation | Design UX | Internal Poster Presentation | Define and Collect Necessary Materials
Revise and Finalize Poster | Design UX | Revise and Finalize Poster | Prototype "App" | Revise and Finalize Poster | Prototype "App" | Revise and Finalize Poster | Finalize Booth | Revise and Finalize Poster | Design UX
| Finalize Booth |  | Proof of Concept |  | Proof of Concept |  | Prototype "App" |  | Finalize Booth
Define and Collect Necessary Materials | Prototype "App" |  | Further development |  | Further development |  | Further development | Define and Collect Necessary Materials | Prototype "App"
Design UX | Further development | Design UX | Algorithms | Design UX | Algorithms | Design UX | Algorithms | Design UX | Dataset
Finalize Booth | Algorithms | Finalize Booth | Introduction Tutorials | Finalize Booth | Literature Review | Finalize Booth | Literature Review | Finalize Booth | Further development
Prototype "App" | Introduction Tutorials | Prototype "App" | Literature Review | Prototype "App" | Model Selection | Prototype "App" | Model Selection | Prototype "App" | Algorithms
| Literature Review | Proof of Concept | Model Selection | Proof of Concept | General Implementation |  | General Implementation |  | Literature Review
| Model Selection |  | General Implementation |  | Tweaking for application |  | Tweaking for application | Dataset | Model Selection
Further development | General Implementation | Further development | Tweaking for application | Further development | Testing, Benchmarking | Further development | Testing, Benchmarking | Further development | General Implementation
Algorithms | Tweaking for application | Algorithms | Testing, Benchmarking | Algorithms | Midterm Presenation | Algorithms | Midterm Presenation | Algorithms | Tweaking for application
Introduction Tutorials | Testing, Benchmarking | Introduction Tutorials | Midterm Presenation |  | Prepare Presentation |  | Prepare Presentation |  | Testing, Benchmarking
Literature Review | Midterm Presenation | Literature Review | Prepare Presentation | Literature Review | Compile Results | Literature Review | Compile Results | Literature Review | Midterm Presenation
Model Selection | Prepare Presentation | Model Selection | Compile Results | Model Selection | Abstract | Model Selection | Abstract | Model Selection | Prepare Presentation
General Implementation | Compile Results | General Implementation | Abstract | General Implementation | Prepare Presentation | General Implementation | Prepare Presentation | General Implementation | Compile Results
Tweaking for application | Abstract | Tweaking for application | Prepare Presentation | Tweaking for application |  | Tweaking for application |  | Tweaking for application | Abstract
Testing, Benchmarking | Prepare Presentation | Testing, Benchmarking |  | Testing, Benchmarking |  | Testing, Benchmarking |  | Testing, Benchmarking | Prepare Presentation
Midterm Presenation |  | Midterm Presenation |  | Midterm Presenation |  | Midterm Presenation |  | Midterm Presenation
Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation
Compile Results |  | Compile Results |  | Compile Results |  | Compile Results |  | Compile Results
Abstract |  | Abstract |  | Abstract |  | Abstract |  | Abstract
Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation |  | Prepare Presentation

## Time Sheet TM1
Workload Fin
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1
Poster and Exhibition Booth
Define Milestones & Packages

## Time Sheet TM2
Workload Stan
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1
Present your schedule

## Time Sheet TM3
Workload Roland
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1

## Time Sheet TM4
Workload Stefan
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
Define Milestones & Packages | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1

## Time Sheet TM5
Workload Jakob
Task | Time Spent (hours) | When | Notes | Total Hours: | 3
other | 2 | 15.4.2015, 16.4.2015
Project Schedule | 1

## temporary
Temporary Sheet for Plan Development
Typ | Name | Description | Result | Start | Duration (days) | Responsible | Team Member 1 | Team Member 2 | Team Member 3 | Team Member 4 | Team Member 5
(M) | Brainstorming phase |  | First Idea, of what we want to do | 2015-04-20 | 1 |  | x | x | x | x | x
(S) | Choose ML Application |  | Application | 2015-04-13 | 7 | all | x | x | x | x | x
(S2) | Set up Project Mgmt | Research and set up Communication, Development und Versioning tools | Working Environment |  | 7 | Stefan |  |  |  | x
(M) | Project Schedule | Develop a project schedule for the whole project. This contains all milestones and the corresponding subtasks in a SMART way. |  | 2015-04-22 | 1 |  | x | x | x | x | x
(S) | Define Milestones & Packages | Define the project's big milestones and put them into this plan. Define the corresponding tasks in a SMART way (this includes time issues, responsibilities, exact task descriptions, description of their result). Discuss whether you need to adapt this template for your individual needs (maybe more columns to describe a task?) | Milestones and Taks are put into your this schedule. | 2015-04-20 | 1 | Stefan | x | x | x | x | x
(S2) | Revise and Finalize Project Plan | Revise your project plan, and send final Version to Andre. | Result --> Andre | 2015-04-21 | 2 | Stefan | x | x | x | x | x
(M) | Poster |  | Poster sent to advisors for printing. Concept and material for booth ready. | 2015-05-10 | 1 | Fin, Jakob
(S1) | Poster Macrodesign |  | Idea of what the poster should look like | 2015-04-22 | 1 | All | x | x | x | x | x
(S2) | Work on Poster Concept |  |  | 2015-04-22 | 5 | Fin, Jakob | x |  |  |  | x
(S1) | Discuss and Finalize Poster Concept |  |  | 2015-04-27 | 1 | Fin, Jakob | x | x | x | x | x
(S2) | Implementation |  | Finalized Poster v1 | 2015-04-27 | 2 | Fin, Jakob | x | x | x | x | x
(S) | Internal Poster Presentation |  | Presentation to Advisor and other Groups | 2015-05-04 | 1 | Fin, Jakob | x | x | x | x | x
(S1) | Revise and Finalize Poster |  | Final Poster | 2015-05-04 | 6 | Fin, Jakob | x | x | x | x | x
(M) | Booth | Develop the booth for the presentation | Booth | 2015-05-11 | 1 | Fin, Jakob
(S) | Define and Collect Necessary Materials |  | All materials ready | 2015-04-20 | 19 | Fin, Jakob | x |  |  |  | x
(S1) | Design UX | Design user experience, think through the workflow | Final Concept | 2015-05-01 | 10 | Fin, Jakob | x | x | x | x | x
(S2) | Finalize Booth |  | Booth | 2015-05-10 | 2 | Fin, Jakob | x | x | x | x | x
(M) | Prototype "App" | Implementation of Eigenface software using existing packages | Working prototype to show at exhibition booth | 2015-05-29 | 1 | Roland, Stan | x | x | x | x | x
(S) | Proof of Concept | Design and implement first version | First Working Program | 2015-04-20 | 7 | Roland, Stan |  | x | x
(S1) | Dataset | Research, Acquire and Clean a dataset for our use | Dataset | 2015-04-20 | 7 | Stefan |  |  |  |  | x
(S2) | Further development | Iterate on the first version | Working program to show at boot | 2015-04-27 | 30 | ? | x | x | x | x | x
(M) | Algorithms | Implement algorithms from Literature, test, tweak, benchmark | Working Implementations of algorithms, benchmarking against other methods | 2015-06-25 | 1 | ? | x | x | x | x | x
(S) | Introduction Tutorials | Prepare a short tutorial on Eigenfaces/Dictionary Learning and present to the group | Short presentations | 2015-04-20 | 3 | Roland, Stan | x | x
(S3) | Literature Review | Read, understand and summarize relevant papers. | relevant knowledge for further project work | 2015-05-01 | 30 | all | x | x | x | x | x
(S) | Model Selection | Get informed about machine Learning, select a few applicable models for our application | know how, model selection | 2015-05-01 | 30 | ? | x | x | x | x | x
(S1) | General Implementation | Implement relevant stochastic algorithms from literature in general form | working general version | 2015-05-29 | 11 | ? | x | x | x | x | x
(S2) | Tweaking for application | Improve and adapt the algorithms for the chosen application, implement interfaces between app, algorithms and ML models | Final Algorithm Implementations | 2015-06-01 | 20 | ? | x | x | x | x | x
(S3) | Testing, Benchmarking | Tweaking models and algorithms, compare algorithms, analytical work | First Results | 2015-06-15 | 10 | all | x | x | x | x | x
(M) | Midterm Presenation |  | Presenting the status quo. | 2015-05-27 | 1 | all | x | x | x | x | x
(S) | Prepare Presentation | see title | Presentation | 2015-05-18 | 7 | all | x | x | x | x | x
(M) | Final Workshop |  | Presentation of your project's results. | 2015-07-11 | 1
(S) | Compile Results | Compile and visualize results of analysis | Results/Charts etc | 2015-06-20 | 8 | all | x | x | x | x | x
(S2) | Abstract |  | Hand in abstract by June 28th. | 2015-06-26 | 3 |  | x | x | x | x | x
(S2) | Prepare Presentation |  |  | 2015-06-28 | 10 |  | x | x | x | x | x