## Sheet1
Date | Hours |  | What?
2015-04-13 | 2 | 2 | Research and set up Project Mgmt Tools
2015-04-14 | 1 | 3
2015-04-15 | 2 | 5
2015-04-18 | 3 | 8 | Research application ideas
2015-04-20 | 6 | 14 | Team Meeting 1, later filled in Project Schedule
2015-04-21 | 2 | 16 | Research Data Sets
2015-04-23 | 5 | 21 | Team Meeting 2: Tutorials & Poster Ideas
2015-04-24 | 2 | 23 | Adapted first datascript from work online
2015-04-27 | 6 | 29 | 3rd Teammeeting: Github and work on Poster Design
2015-04-29 | 9 | 38 | Worked on poster implementation, fixed problems in repository
2015-05-06 | 1.5 | 39.5 | Poster
2015-05-08 | 10 | 49.5 | Poster
2015-05-10 | 9.5 | 59 | Poster
2015-05-17 | 3 | 62 | Reading Papers
2015-05-18 | 1.5 | 63.5 | 4th Meeting (Boulderworld)
2015-05-19 | 1 | 64.5 | Implementing SQN algorithm
2015-05-27 | 3 | 67.5 | Implementing SQN algorithm
2015-06-01 | 2 | 69.5 | 5th Meeting: Revise project schedule, tasks
2015-06-08 | 10 | 79.5 | SQN implementation, debugging
2015-06-10 | 9 | 88.5 | Team Meeting, coding session at Stans house + debugging SQN
2015-06-15 | 1.5 | 90 | Meeting with Andre
2015-06-21 | 7 | 97 | Coding / Reading / Understanding Session bei Fin
2015-06-22 | 5 | 102 | Coding session Garching Hochbrück, Debugging, Higgs Dataset
2015-06-23 | 2 | 104 | Went through sklearn implementation of SGD to understand all their optimization tricks
2015-06-24 | 2 | 106 | Worked on Higgs dataset splitting
2015-06-26 | 9 | 115 | Coding Session Nordgelände, Python 2.7/3.4 stuff, SQL
2015-06-28 | 3 | 118 | SQL stuff, abstract
2015-06-29 | 6 | 124 | Meeting: Discussion Presentation, more SQL, reverted from 3.4 to 2.7
2015-06-30 | 4 | 128 | Integrated Stan's dataset, explained evolved code architecture to Stan, stationarity test with Jakob, reconstructed hours of last week
2015-07-04 | 9 | 137 | Coding session at Stan's house: Planning, set up LaTeX templates, made outline of presentation, debugging, testing of SQN
2015-07-05 | 8 | 145 | Cleaning Project Code structure, worked on slides, set up plotting tools, testing and analysis on EEG and SQN
2015-07-06 | 6 | 151 | SQN with SQL testing, made slides
2015-07-07 | 3 | 154 | Slides, Meeting with Andre, SQN tests
2015-07-08 | 12 | 166 | Planning and implementation of final SQN benchmarking suite
2015-07-09 | 6 | 172 | Preparation of Presentation, final benchmarks
2015-07-10 | 12 | 184 | Preparation of Presentation